## Risk Register
Risk ID | Rank | Risk Event | Category | Root Cause / Trigger | Probability | Impact | Response | Risk Owner (proposed) | Preventive / Acceptance Action | Contingency if occurs
R01 | 1 | External API unavailability | External | Data.gov.sg or OneMap outage; failed or rate-limited requests | Medium | High | Mitigate | Backend Developer | Monitor API availability, validate responses, handle failures | Use previously validated cached data where permitted; label freshness
R02 | 2 | Inaccurate or outdated housing information | External | Source data lag, inconsistency, missing values | Medium | High | Mitigate | Backend Developer / QA Manager | Validate source data and monitor dataset updates | Show data freshness; flag unavailable or unverified information
R03 | 3 | Frontend and backend integration failures | Technical | Mismatched interfaces or service contracts; failed integration tests | Medium | High | Mitigate | Frontend / Backend Developers | Agree API contracts, test integrations early | Prioritise affected core integrations and correct interface mismatches
R04 | 4 | Development schedule delays | Project Management | Underestimated work or unforeseen technical difficulties | Medium | High | Mitigate | Project Manager | Track milestones in GitHub Kanban and prioritise critical tasks | Reallocate work and adjust lower-priority activities through change control
R05 | 5 | Inaccurate AI chatbot responses | Technical | LLM outputs unsupported or misleading housing content | Medium | High | Mitigate | QA Manager / Backend Developer | Validate responses against available data; constrain unsupported outputs | Direct users to verified information; suspend affected chatbot functionality
R06 | 6 | Release of incorrect personalised ranking results | Technical | Incorrect score calculations or weighting logic; failed ranking tests | Medium | Medium | Avoid | QA Manager / Release Manager | Block release until critical ranking tests pass; verify weights and expected outputs | Disable ranking and retain standard filtering until corrected
R07 | 7 | Limited team availability | People and Resources | Unexpected absence or temporary capacity reduction | Medium | Medium | Accept | Project Manager | Accept possibility of absence and monitor availability | Redistribute critical tasks and adjust task priorities
R08 | 8 | Insufficient testing time | Project Management | Development delays compress the testing window | Medium | Medium | Mitigate | QA Manager / QA Engineer | Start testing early; prioritise critical test coverage | Prioritise essential regression and acceptance tests; escalate schedule risk
R09 | 9 | Application performance issues | Technical | Large datasets, numerous markers or inefficient queries | Medium | Medium | Mitigate | Frontend / Backend Developers | Optimise data queries and rendering; performance test realistic loads | Reduce displayed markers / queries and prioritise performance fixes
R10 | 10 | Unexpected AI API or hosting costs | Financial | Usage volume or hosting expenses exceed estimate | Low | Medium | Mitigate | Project Manager / Backend Developer | Monitor consumption and spending; apply usage limits | Limit non-critical AI functionality or usage and review hosting options

## Top 10 Tracking
Risk ID | Current Rank | Owner (proposed)
R01 | 1 | Backend Developer
R02 | 2 | Backend Developer / QA Manager
R03 | 3 | Frontend / Backend Developers
R04 | 4 | Project Manager
R05 | 5 | QA Manager / Backend Developer
R06 | 6 | QA Manager / Release Manager
R07 | 7 | Project Manager
R08 | 8 | QA Manager / QA Engineer
R09 | 9 | Frontend / Backend Developers
R10 | 10 | Project Manager / Backend Developer

## Guide
HDBUDDYPRO — RISK MANAGEMENT LOG v1.0
Basis | Risk Management Plan v2.0 (latest document supplied)
Important | All probabilities, impacts, rankings and risk owners are proposed for team confirmation. No actual risk occurrence or completed mitigation is claimed.
Probability (plan) | Low: below 30%; Medium: 30–70%; High: greater than 70%.
Impact | High / Medium / Low according to Section 2.3.1 in the Risk Management Plan.
Risk prioritisation | Rankings follow the plan's Top 10 list. For equal qualitative ratings, team judgement considers impact on critical functions, dependencies and recovery effort.
Response strategies | Mitigate: reduce likelihood/impact. Avoid: prevent known incorrect ranking release. Accept: acknowledge absence risk, monitor, and use contingency if triggered.
Quantitative exposure | The plan's Section 2.3.2 defines Exposure = estimated probability × estimated impact (hours/cost). No risk-specific quantitative exposure has been invented in this log.
Risk Register | Update the owner, status, triggers, preventive/contingency measures and review date as the project progresses.
Top 10 Tracking | Previous rank, periods in list and progress are blank or pending until real periodic reviews occur.
Version | 1.0 — initial proposed register prepared against current Risk Management Plan.